## Sheet1
Area | Issue | Spec affected | Effort | Mockup (Y/N) | Notes | Status
Font Loading Strategy Details Missing | How exactly are fonts loaded in preview/export? CSS @font-face? Web Font Loader? | font-handling-spec.md | High | N |  | Complete
Font Loading Strategy Details Missing | No mention of CORS handling for external URLs | font-handling-spec.md | High | N |  | Complete
Font Loading Strategy Details Missing | Missing font loading timeout strategies | font-handling-spec.md | Medium | N |  | Complete
Font Loading Strategy Details Missing | No guidance on font display behavior (swap, fallback, block) | font-handling-spec.md | Medium | N |  | Complete
Storage Architecture Unclear | How are uploaded fonts stored in Supabase? File storage? Base64 in database? | font-handling-spec.md | High | N |  | Complete
Storage Architecture Unclear | No file size limits specified for uploads | font-handling-spec.md | Medium | N |  | To do
Storage Architecture Unclear | Missing font file validation beyond file extension | font-handling-spec.md | Medium | N |  | Complete
Performance Considerations Underspecified | No mention of font preloading strategies | font-handling-spec.md | Medium | N |  | Complete
Performance Considerations Underspecified | Missing font subsetting considerations | font-handling-spec.md | Medium | N |  | Complete
Performance Considerations Underspecified | No guidance on font file optimization | font-handling-spec.md | Medium | N |  | Complete
User Experience Gaps | How do Template Editors preview fonts before assignment? | font-handling-spec.md | Medium | Y |  | Complete
User Experience Gaps | No mention of font loading indicators | font-handling-spec.md | Medium | Y |  | Complete
User Experience Gaps | Missing error messaging for font failures | font-handling-spec.md | Medium | Y |  | Complete
Font Loading Strategy Details Missing | How to implement Google Fonts | font-handling-spec.md | High | N |  | Complete
Font Loading Strategy Details Missing | Add Robust Fallback Strategy | font-handling-spec.md | Medium | N |  | Complete
Font Loading Strategy Details Missing | Font Loading Detection | font-handling-spec.md | High | N |  | Complete
Font Loading Strategy Details Missing | Font Storage Strategy | font-handling-spec.md | High | N |  | Complete
Template Conflict Resolution | When a Contributor has manual formatting and switches templates, what's the exact behavior? | template-system-spec.md | Medium | Y |  | Complete
Template Conflict Resolution | How do we handle edge cases like custom font sizes that don't exist in the new template? | template-system-spec.md | Medium | N |  | Complete
Template Conflict Resolution | Should we show a diff or warning when template switches would dramatically change appearance? | template-system-spec.md | High | Y |  | Complete
Document Structure & Smart Style Inference | The smart style inference spec mentions AI classification - is this truly needed for MVP? | smart-style-inference-spec.md | Critical | N |  | To do
Document Structure & Smart Style Inference | Can we achieve good results with just heuristic detection initially? | smart-style-inference-spec.md | Critical | N |  | To do
Document Structure & Smart Style Inference | How do we handle ambiguous content that could be either a heading or emphasized paragraph? | smart-style-inference-spec.md | Critical | N |  | To do
Role Switching & Context | When Template Editors switch between creating templates and writing documents, how do we maintain context? | roles-and-permissions.md | Medium | N |  | To do
Role Switching & Context | Should we save drafts separately for each role context? | roles-and-permissions.md | High | N |  | To do
Role Switching & Context | How do we handle notifications and recent items across role contexts? | roles-and-permissions.md | Medium | N |  | To do
Guest Mode Limitations | The guest journey mentions 20-minute sessions - is this enough for meaningful demos? | guest-role-emulation-spec.md | Low | N |  | To do
Guest Mode Limitations | Should guests be able to export/save anything, or is it purely exploratory? | guest-role-emulation-spec.md | Medium | N |  | To do
Guest Mode Limitations | How do we convert engaged guests to paid users effectively? | guest-role-emulation-spec.md | Medium | N |  | To do
Feature Completeness | The reusable toolbar spec lists many 'Coming Soon' features - might this make MVP feel incomplete? | reusable-toolbar-spec.md | Medium | Y |  | To do
Feature Completeness | Should we hide unimplemented features entirely or show them as planned? | reusable-toolbar-spec.md | Low | N |  | To do
Feature Completeness | What's the minimum feature set that still delivers the core value proposition? | reusable-toolbar-spec.md | High | N |  | To do
Success Metrics | How will we measure if the 'separation of concerns' philosophy actually works? | product-vision.md | High | N |  | To do
Success Metrics | What metrics indicate Template Editors are successfully creating usable templates? | template-system-spec.md | Medium | N |  | Complete
Success Metrics | How do we know Contributors aren't frustrated by the formatting limitations? | contributor-template-behavior-spec.md | Medium | N |  | To do
Guest Role Implementation | Make Simpler: Toggle demo mode in localStorage, load mock data, disable save/export, show 'Demo Mode' indicator, reset on refresh | guest-role-emulation-spec.md | Critical | N |  | To do
Tiptap Editor | Specify Tiptap version and enumerate all required extensions | editor-spec.md | High | N | Must include custom, third-party, and MVP-only extensions in spec | To do
Admin | Update Mylo_Mocks_Directory.csv file and fix paths |  | Low | N | Ensure all mock file paths are current and consistently named | To do
User Role Management | How will user roles be determined? Is this hardcoded for MVP, passed as props, or stored in state/context? | roles-and-permissions.md | Critical | N |  | To do
User Role Management | Should users be able to switch roles in the same session, or is this determined at login? | roles-and-permissions.md | Medium | N |  | To do
User Role Management | What should be the fallback role when no role is specified? | roles-and-permissions.md | Medium | N |  | To do
Data Persistence & API Integration | Are we using mock data, localStorage, or do you have API endpoints ready? | deployment-manual.md | Critical | N |  | To do
Data Persistence & API Integration | What exact JSON structure should documents be saved in? | mylo-api-document-save-spec.md | Critical | N |  | To do
Data Persistence & API Integration | How are templates stored and retrieved? | mylo-api-template-save-spec.md | Critical | N |  | To do
Data Persistence & API Integration | How often should auto-save trigger? | autosave-spec.md | Critical | N |  | To do
Template System Specifics | Should there be UI indication when Template Settings change and affect existing styles? | template-settings-spec.md | Medium | Y |  | Complete
Template System Specifics | What happens if a template is deleted while documents are using it? | template-system-spec.md | High | N |  | Complete
Template System Specifics | What are the heuristic rules for determining headings, body text, and callouts? | smart-style-inference-spec.md | Medium | N |  | To do
Navigation & Routing | Should each workspace (Contributor/Template Editor/Admin) be separate routes or conditional components? | routing-spec.md | Critical | N |  | To do
Navigation & Routing | Do we need URLs for specific documents/templates? | routing-spec.md | Critical | N |  | To do
Navigation & Routing | How does login/logout integrate with role-based access? | authentication-spec.md | Critical | N |  | To do
Tiptap Integration Specifics | What exact node types should the Tiptap editor support? | editor-spec.md | High | N |  | To do
Tiptap Integration Specifics | Which Tiptap extensions are must-have vs nice-to-have for MVP? | editor-spec.md | High | N |  | To do
Tiptap Integration Specifics | Any concerns about real-time preview rendering performance? | editor-preview-spec.md | Medium | N |  | To do
UI/UX Behavior Details | At what screen sizes should the layout change (e.g., tablet view)? | responsive-layout-spec.md | Medium | Y |  | To do
UI/UX Behavior Details | How should the app handle Tiptap editor crashes or save failures? | error-handling-spec.md | High | N |  | To do
UI/UX Behavior Details | What should users see while templates load or documents save? | loading-states-spec.md | Medium | Y |  | To do
MVP Scope Boundaries | Should disabled features (like AI classification) show 'Coming Soon' or be completely hidden? | mvp-scope.md | Low | N |  | To do
MVP Scope Boundaries | What happens when templates fail to load or apply? | template-system-spec.md | Medium | N |  | Complete
MVP Scope Boundaries | Any specific browser support requirements? | deployment-manual.md | Low | N |  | To do
Data Structure Validation | How detailed should the version history be for MVP? | document-versioning-spec.md | Medium | N |  | To do
Data Structure Validation | PDF export - any specific formatting or metadata requirements? | pdf-export-spec.md | High | N |  | To do
Data Structure Validation | Are we starting with system fonts only, or do we need web font loading? | font-handling-spec.md | High | N |  | Complete
Business Logic | Can Contributors see Template Editor workspaces or vice versa? | roles-and-permissions.md | Medium | N |  | To do
Business Logic | Who can access which templates? | template-system-spec.md | Medium | N |  | Complete
Business Logic | Is real-time collaboration needed for MVP, or single-user editing only? | collaboration-spec.md | High | N |  | To do
Integration Points | Are you planning to use the Supabase integration mentioned in the useful context? | deployment-manual.md | Medium | N |  | To do
Integration Points | For images in Template Editor - where should these be stored? | image-handling-spec.md | Medium | N |  | To do
Integration Points | PDF generation - client-side or server-side? | pdf-export-spec.md | High | N |  | To do